## Slide 1: Estimate Activity Duration - Inputs
- Project Schedule Management

## Slide 2
Estimate
Activity
Duration
–
Inputs
Project Management Plan
Schedule Management Plan: estimation methods, tools/calendars, update cadence.
Scope baseline (scope statement, WBS, WBS dictionary) driving decomposition and constraints.
Resource and risk strategies informing availability, buffers, and mitigation approach.
Project Documents
Activity list & attributes; assumption log; lessons learned register to calibrate estimates.
Resource data: team assignments, resource requirements, RBS, and resource calendars for capacity and timing.
Milestones & risk register to anchor deadlines, dependencies, and contingency needs.
Enterprise Environmental Factors (EEFs)
Organization: culture/structure, working-time norms, infrastructure influencing throughput.
External constraints: market conditions, regulatory windows, vendor lead times.
Tooling/standards: estimating databases, productivity baselines, industry benchmarks.
Organizational Process Assets (OPAs)
Historical durations, benchmarks, templates, and checklists for consistent estimating.
Policies/procedures for estimating, contingency rules, and reporting formats.
PMIS repositories and prior project data to validate and refine duration assumptions.